A HEALTH PROMOTION FOUNDATION IN BRITISH COLUMBIA

Timelines

| TASK | Development Phase |  |  | Year One |  |
| --- | --- | --- | --- | --- | --- |
|  | Months 1-3 | Months 3-6 | Months 6-9 | Months 9-16 | Months 16-18 |
| Set up leadership team |  |  |  |  |  |
| Organize working committees |  |  |  |  |  |
| Define Fdn. values, mission, goals, objectives and operating principles |  |  |  |  |  |
| Work with Government to prepare Legislation |  |  |  |  |  |
| Determine minimal criteria for funding community projects |  |  |  |  |  |
| Research project re: most effective funding allocation process |  |  |  |  |  |
| Define Board, committee structures, relationships with other stakeholders |  |  |  |  |  |
| Solicit names for Board |  |  |  |  |  |
| Transition to Board |  |  |  |  |  |
| Internal evaluation of developmental phase process and accomplishments |  |  |  |  |  |
| Pilot models in 5 regions |  |  |  |  |  |
| Evaluate pilot project |  |  |  |  |  |
| External evaluation of Foundation |  |  |  |  |  |
| Develop evaluation framework for community grants process |  |  |  |  |  |